Family Justice Council

2022 – 2023 Business Plan

| Activity 1: Use of covert recordings in family law proceedings concerning children |  |
| --- | --- |
| Led by: Natasha Watson and Jaime Craig – with Maud Davis, Jenny Beck, Ruth Henke, Mavis Amonoo-Acquah and Karen Venables |  |
| Time Scale | April 2019 – |
| Objective | To consider the issues arising from covert recording from a multi-disciplinary viewpoint, and thereafter to make recommendations as to the formulation of FJC guidance. |
| Outcome: The development of guidance to encourage good practice in relation to the recordings of children and professionals so as to potentially diminish the need for covert recordings. |  |
| Next steps: - The draft guidance has been sent to stakeholders for consultation. The closing date is 16.30 on 12 December 2022. |  |

| Activity 2: Communication and dissemination of FJC work. |  |
| --- | --- |
| Led by: Secretariat, Natalia Schiffrin and members |  |
| Time Scale | April 2019 – |
| Objective | To publicise the FJC and its work and to consider its role in signposting to online information. |
| Outcome: Increased awareness of FJC business and improved use of the FJC webpages and other resources to enable better access and navigation of the family court for LiPs and stakeholders. |  |
| Next steps: - Implement communications strategy to promote Council business - ongoing - Continuing review of the information on the FJC website to ensure that it is up to date and accessible all users. - Assess website usage using Google Analytics. |  |

| Activity 3: Domestic Abuse |  |
| --- | --- |
| Led by: Rosemary Hunter - with Melanie Carew, Matthew Pinnell, Natasha Watson, Judith Crisp, Jaime Craig, Jenny Beck, Judith Crisp and Karen Venables |  |
| Time Scale | April 2019 – |
| Objective | To monitor the operation of the family justice system in relation to domestic abuse from an interdisciplinary perspective. To respond to consultations and advise on areas for potential further work. |
| Outcome: Addressing issues arising in relation to domestic abuse in the family courts. |  |
| Next steps: The Family Justice Council has decided that the work being undertaken by the Domestic Abuse working group on producing a best practice guidance will cease in light of the many dynamic changes impacting on the courts in this area and more generally, which have meant that the production and reception of new guidance is no longer feasible. The President would like to thank the working group for the considerable amount of work undertaken by them on the draft guidance, which has also informed the Council’s consultation responses, Judicial College training sessions and the information provided to litigants by HMCTS, resulted in guidance on safety from domestic abuse and special measures in remote and hybrid hearings, and raised awareness and promoted discussion of good practices through two rounds of consultation. Thanks are also due to those individuals and organisations who responded to the consultations, and whose responses have been immensely helpful to the working group and to the work of the Council more generally. The President would like to affirm the Council’s ongoing commitment to ensuring that domestic abuse is properly understood and responded to in family courts and welcomes that the working group will continue to contribute its multi-disciplinary expertise to respond to consultations and to keep the area of domestic abuse under continuing review. The working group aim to meet again in late January/early February 2023. |  |

| Activity 4: Experts in the family justice system |  |
| --- | --- |
| Led by: David Williams - with Jaime Craig, Fiona Straw, Maud Davis and Colette Dutton |  |
| Time Scale | May 2019 – |
| Objective | To oversee the national implementation of recommendations emerging from the President’s Experts Working Group. - Responsible for the delivery of training and mentoring at a regional level. - Set up and supervise local committees across England and Wales. - Enable two-way channels of communication, information and support. |
| Outcome: To promote the work of medical and health experts in the family justice system. |  |
| Next steps: - Forge links with other bodies - in progress - Consider report’s other recommendations – sub-groups and action plans confirmed - Re-invigorate mini-pupillage scheme – in progress - Date of next working group: 10 January 2022 |  |

| Activity 5: Death by Suicide within Family Proceedings: Awareness and support |  |
| --- | --- |
| Led by: Chair Colette Dutton - with Annie Bertram, Judith Crisp, Jenny Beck, Maud Davis, Fiona Straw, Jaime Craig, Rebecca Cobbin, Matthew Pinnell and Bernadette MacQueen. |  |
| Time Scale | April 2021 - |
| Objective | To investigate the risk and resilience factors for suicide and self-harm and to consider what training would be helpful to support the judiciary and court participants. |
| Outcome: Best practice guidance and training and support for litigants and judiciary. |  |
| Next steps: - The aim is to prepare guidance ready for December 2022. |  |

| Activity 6: Responding to allegations of alienating behaviour |  |
| --- | --- |
| Led by: Jaime Craig and Karen Venables – with Jenny Beck, Rosemary Hunter, Claire Webb, Fiona Straw, Melanie Carew, Matthew Pinnell, Bernadette MacQueen, Mavis Amonoo-Acquah and Natalia Schiffrin. |  |
| Time Scale | January 2022 – early 2023 |
| Objective | To consider the issues arising from allegations of Alienating behaviour from a multi-disciplinary viewpoint |
| Outcome: Develop FJC Guidance as to how these complex allegations are responded to by the family courts |  |
| Next steps: - The working group will work to a 12-month timetable, allowing approximately 4-5 months for the development of draft guidance, a period of external consultation and revision before a final draft being presented to the January meeting of the council 2023. - The working group is planning to hold a face to face meeting on 23 January to discuss progress on the draft. |  |

| Activity 7: Financial Remedies |  |
| --- | --- |
| Led by: Mr Justice Peel – with Judith Crisp. |  |
| Time Scale | January 2022 - |
| Objective | An ad hoc committee to respond to financial remedy matter as and when they arise. |
| Outcome: Examples include: - Responses to consultations - Updating the financial remedy guidance on the website - Being on hand to help the FRC such as helping to draft information guidance - Any wider FJC work which would benefit from some financial remedy input |  |
| Next steps: - The group is reviewing and updating the guidance on ‘Sorting out Finances on Divorce’ and ‘Guidance on Financial Needs on Divorce’. - The aim is to have up to date versions ready for discussion at the next meeting of the main group on 14 December 2022. |  |

| Activity 8: Medical Treatment Cases |  |
| --- | --- |
| Led by: Melanie Carew – with Ruth Henke, Fiona Straw, Maud Davis and Claire Webb |  |
| Time Scale | July 2022 – |
| Objective | To develop guidance (aimed at solicitors, hospitals, courts and parents) on applications for orders in relation to medical treatment of children. |
| Outcome: Guidance on best practice for applications for treatment orders relating to children. |  |
| Next steps: - A draft copy of the guidance has been circulated to members for comment. - The draft guidance will be sent to other organisations for comment in December 22. - The working group will meet again once the document has been through these stages. |  |

November 2022